## Start Here
🏠 Renovation OS — Start Here
What this tab does: set up your project once (yellow cells), then follow the 5 steps on the right.
YOUR PROJECT |  |  | GET STARTED IN 10 MINUTES
Project name |  | Shown as the Dashboard title. | 1 | Fill in the yellow cells on the left
Property address |  | For your own reference. |  | Project dates, total budget, currency, tax. Everything else calculates itself.
Project start date |  | First day of the project (design counts!). The Timeline starts here. | 2 | Budget tab: set a budget per category
Target move-in date |  | The date you want to live in the house again. |  | Rename categories if you like. Aim for the total to match your working budget.
|  | Everything you can spend, including tax and your safety buffer. | 3 | Contractors + Quotes: add who you work with
|  | Optional — used for cost per m² / ft². |  | Compare quotes side by side — the hidden-cost checklist shows the TRUE price.
“Today” override (optional) |  | Leave EMPTY to use today's date. | 4 | Timeline: set durations and dependencies
Dates, Gantt chart and order-by dates for your materials follow automatically.
PREFERENCES |  |  | 5 | Every Monday open Dashboard + This Week
Currency | USD $ | Shown next to every amount header. Pick ‘Other’ to type your own symbol. |  | Do the ranked actions. On Friday fill the Friday Review. That's the whole routine.
Custom currency symbol |  | Only used when Currency = Other.
Tax name | Sales tax | VAT, Sales tax, GST… used in labels.
Default tax rate | 8% | Used to add tax to quotes entered WITHOUT tax. | COLOUR LEGEND
Prices usually quoted incl. tax? | Yes | Pre-fills each quote; you can still change it per quote. |  | Light-yellow cell = YOU TYPE HERE (or pick from the dropdown).
Area unit | ft² | m² or ft² for room sizes. |  | White / grey cell = automatic. Protected so you can't break a formula.
Week starts on | Sunday | Used by This Week and the Gantt chart. | 🟢 | On track — nothing to do.
Budget ‘attention’ band | 5% | A budget line turns 🟡 when forecast is over budget by up to this %, 🔴 above. | 🟡 | Needs attention soon (within your alert window).
|  |  | 🔴 | Urgent — overdue, over budget or at risk.
ALERT SETTINGS |  |  |  | Sheets are protected without a password: Review ▸ Unprotect sheet if you really need to change a formula.
Contingency (safety buffer) % | 10% | 10–15% is typical. Kept aside from your total budget.
Alert window (days) | 7 | Things due within this many days show as 🟡 ‘this week’. | YOUR TABS
Decide-before-order buffer (days) | 7 | Decide this many days before the order-by date. | ▸ | Dashboard | Your renovation at a glance + ranked next actions.
Order safety buffer (days) | 5 | Extra days between delivery and installation. | ▸ | This Week | Monday plan and Friday review.
Overpayment tolerance % | 10% | Warn when paid % is more than this ahead of work done %. | ▸ | Budget | Budget vs committed vs forecast per category.
|  |  | ▸ | Quotes | Compare up to 4 quotes per trade, incl. hidden costs.
CALCULATED FOR YOU |  |  | ▸ | Contractors | Contractors, overpayment check and communication log.
|  | Kept aside for surprises — not part of your working budget. | ▸ | Payments | Payment schedule, invoices and 12-month cash flow.
|  | What you plan to spend. Budget lines should add up to this. | ▸ | Change Orders | Change orders with impact preview before you approve.
Currency symbol in use |  |  | ▸ | Timeline | Tasks, dependencies and Gantt chart.
Today (as used by all tabs) |  |  | ▸ | Rooms | One card per room: money, progress, problems.
Tax word used in labels |  |  | ▸ | Selections & Orders | Decisions and orders — with decide-by and order-by dates.
|  |  | ▸ | Issues & Punch List | Problems found on site and the final punch list.
|  |  | ▸ | Vault | Links to every document and photo + what is missing.
|  |  | ▸ | Warranty & Maintenance | Warranties and home maintenance after the renovation.
Note on B9: Your total renovation budget including tax. Renovation OS keeps the contingency % aside as a safety buffer, the rest is your working budget.
Note on B11: Normally empty. Type a date here to see the workbook as it was/will be on that date. The demo file is frozen on a date so every feature shows data.
Note on B17: When a quote says prices exclude tax, Quotes adds this rate so all quotes are compared like-for-like.
Note on B24: Money you keep aside for surprises. Working budget = total budget − contingency.
Note on B26: Time you want between making a decision (e.g. choosing tiles) and placing the order.
Note on B27: Order-by = needed-on date − supplier lead time − this buffer.
Note on B28: Protects you from paying ahead of progress. Example: 10% means paying 50% for 35% of the work triggers a warning.

## Dashboard
What this tab does: your renovation at a glance — updated automatically. Nothing to type here. |  |  |  |  | As of
|  |  | Contingency used | Project day |  | Time elapsed
Forecast move-in |  | Open issues | Overdue items | Decisions waiting |  | Orders due
RENOVATION HEALTH
Budget
Timeline
Contractors & payments
Materials
Decisions
Issues
YOUR NEXT ACTIONS — ranked by urgency
# | Priority | What to do |  | Where |  | Due | When
CHARTS

## This Week
🗓️ This Week
What this tab does: Monday — see everything that falls in this week. Friday — review what happened and write down next week's top 3.
Week starting |  | Tip: overwrite the yellow date to look at another week.
Week ending
📋 MONDAY PLAN — what falls in this week
Decisions to make |  | Selections with a decide-by date this week
Orders to place |  | Chosen items with an order-by date this week
Payments due |  | Unpaid payments with a due date this week
Deliveries expected |  | Orders arriving this week — someone must be on site
Tasks starting |  | Timeline tasks starting
Tasks finishing |  | Timeline tasks due to finish
Issues with an action this week
🔴 TOP 10 ALERTS DUE BY THE END OF THIS WEEK (incl. overdue)
Priority | Due | What to do | Where | When
📝 FRIDAY REVIEW — the numbers (automatic)
Change orders approved this week
Tasks completed this week
Issues opened this week
Issues closed this week
📝 FRIDAY REVIEW — your notes (type in the yellow boxes)
What was completed?
What was delayed?
What changed?
What is now at risk?
Top 3 for next week
Note on C4: Shows the current week automatically. Type any date to plan another week (to go back, type =AsOf or re-download the formula from the guide).

## Budget
💶 Budget
What this tab does: compares your budget per category with what you have committed, invoiced and paid, and forecasts the final cost.
Sum of category budgets
Category | Stage |  | Status | lvl | chart key
Demolition | Estimating
Structural | Estimating
Plumbing | Estimating
Electrical | Estimating
HVAC | Estimating
Windows & doors | Estimating
Roofing | Estimating
Kitchen | Estimating
Bathrooms | Estimating
Flooring | Estimating
Painting | Estimating
Landscaping | Estimating
Furniture | Estimating
Appliances | Estimating
Permits | Estimating
Professional fees | Estimating
Waste removal | Estimating
Other | Estimating
TOTAL
RISK — what could still come on top of the forecast
Pending change orders (not approved yet)
Estimated cost of open issues
RISK (could still be added)
FORECAST INCL. RISK
Contingency used by forecast
Note on B7: Rename, add or clear categories (up to 30). They feed every Category dropdown in the workbook.
Note on D7: Estimating = still collecting quotes. Contracted = contract signed. Complete = work finished and final invoice received.
Note on E7: Lowest TRUE cost (incl. hidden costs) from the Quotes tab for this category.
Note on F7: Sum of SIGNED contracts on the Contractors tab with this category.
Note on G7: Materials you buy yourself: selected option prices on Selections & Orders.
Note on H7: Approved change orders for this category.
Note on I7: Contracted + materials + approved changes: money you have promised to spend.
Note on L7: Estimating: the highest of budget, best quote, committed and invoiced (be pessimistic until signed). Contracted/Complete: committed (or invoiced if higher).
Note on M7: Budget − forecast. Negative (red) = over budget.

## Quotes
⚖️ Quotes
What this tab does: compares up to 4 contractors per trade side by side and reveals the TRUE cost once hidden extras are added.
SCORING WEIGHTS (points, should total 100)
| Price | Timeline | Warranty | Checklist | Gut & refs | Total
Cheapest TRUE cost, shortest timeline and longest warranty get full points; others get proportional points. | 40 | 20 | 15 | 15 | 10
Tip: type prices exactly as quoted. Yellow checklist cells: estimate what a missing item will cost you — it is added to the TRUE COST.
[8 empty] | block cat | best true | 1/best | warn | expiry due | pri | text
COMPARISON 1 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 2 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 3 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 4 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 5 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 6 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 7 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 8 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 9 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
COMPARISON 10 ▸ trade:
| Contractor 1 |  | Contractor 2 |  | Contractor 3 |  | Contractor 4
Contractor / company
Timeline (weeks)
Warranty (years)
References checked?
Gut feeling (1–5)
Quote valid until
HIDDEN-COST CHECKLIST | Included? |  | Included? |  | Included? |  | Included?
Demolition
Waste disposal
Delivery
Permits
Materials specified
Labor specified
Finishing
Cleanup
Electrical upgrades
Plumbing modifications
Payment schedule defined
Warranty in writing
Completeness
SCORE
Price points
Timeline points
Warranty points
Completeness points
Gut & references points
TOTAL SCORE
Ranking
Note on B13: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B18: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B19: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B35: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B36: Share of the 13 checklist items marked Included.
Note on B52: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B57: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B58: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B74: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B75: Share of the 13 checklist items marked Included.
Note on B91: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B96: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B97: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B113: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B114: Share of the 13 checklist items marked Included.
Note on B130: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B135: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B136: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B152: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B153: Share of the 13 checklist items marked Included.
Note on B169: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B174: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B175: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B191: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B192: Share of the 13 checklist items marked Included.
Note on B208: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B213: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B214: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B230: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B231: Share of the 13 checklist items marked Included.
Note on B247: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B252: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B253: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B269: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B270: Share of the 13 checklist items marked Included.
Note on B286: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B291: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B292: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B308: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B309: Share of the 13 checklist items marked Included.
Note on B325: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B330: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B331: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B347: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B348: Share of the 13 checklist items marked Included.
Note on B364: Yes = the price already includes tax. No = Renovation OS adds your default tax rate (Start Here) so quotes compare like-for-like.
Note on B369: 1 = bad feeling, 5 = great. Trust matters on a 6-month job.
Note on B370: Expiry date written on the quote. You get an alert before it expires (unless the category is already Contracted).
Note on B386: Price incl. tax + all estimated hidden extras. This is what the job will really cost you.
Note on B387: Share of the 13 checklist items marked Included.

## Contractors
👷 Contractors
What this tab does: one row per contractor — contract, paperwork, progress and a warning when you pay ahead of the work. Communication log below.
Company | Trade | Budget category | Main room | Contact person | Phone | Email |  |  |  | Contract signed? | Start | Expected completion | Insurance ✓ | License ✓ | Warranty (years) | % work complete | Paid % | Overpayment check | lvl | due | pri | text
COMMUNICATION LOG — every call, email and site conversation. Follow-ups turn into alerts.
Contractor | Date | What was said / agreed |  |  |  |  | Follow-up needed? | Follow-up date | Follow-up done? | [10 empty] | due | pri | text
Note on D5: Links this contract to a Budget line.
Note on E5: Where most of their work happens (or Whole house). Used by the Rooms tab.
Note on I5: Signed contract amount incl. tax (without later change orders).
Note on L5: Only signed contracts count as Committed on the Budget.
Note on O5: Have you seen a valid liability insurance certificate?
Note on P5: Registered / licensed for this trade where required?
Note on R5: YOUR estimate of how much of their work is done. Update weekly — it drives the overpayment check.
Note on U5: ⚠️ appears when paid % is ahead of work complete % by more than your tolerance (Start Here).

## Payments
💳 Payments
What this tab does: your payment schedule, invoices and payments per contractor — plus a 12-month cash-flow forecast (right side →).
PER-CONTRACTOR SUMMARY
Paid to (contractor / supplier) | Milestone / what for | Room (optional) | Category (if not a contractor) | % of contract | Due date | Invoice # | Invoice date | Paid date | Status | Category (auto) | room | lvl | unpaid | 1/due | due | pri | text | Contractor | Next payment
CASH FLOW — 12 months from project start
Month
Note on B5: Pick a contractor, or type any supplier name (you'll get a warning you can accept).
Note on D5: Leave empty to use the contractor's main room.
Note on E5: Only needed for suppliers that are not on the Contractors tab, so the payment lands on the right Budget line.
Note on F5: Milestone as % of the contract value…
Note on G5: …or a fixed amount (wins over %).
Note on M5: Enter the date you paid — this marks the row as Paid.
Note on AC38: All unpaid amounts due in the next 30 days, including anything overdue.

## Change Orders
🔁 Change Orders
What this tab does: logs every change to the plan and previews its effect on budget, contingency and move-in date BEFORE you approve it.
⚠️ Never approve a change without checking this preview → the grey columns show your forecast, contingency and move-in date IF you approve.
CO # | Date requested | Requested by | Contractor | Budget category | Room | What changes | Reason | Extra days | Status | Decision date | Move-in if approved | vs working budget | lvl | due | pri | text
Note on J6: Extra cost incl. tax. Use a negative number for savings.
Note on K6: How many days this adds. After approving, also add these days as Delay on the affected Timeline task.
Note on N6: Budget forecast total including this change (already included if Approved).

## Timeline
📅 Timeline
What this tab does: tasks with durations and dependencies → start/end dates, late warnings and a 52-week Gantt chart. Forecast finish feeds the Dashboard.
| Forecast finish |  | Target move-in | [17 empty] | Gantt: teal = planned · grey = done · red = late · yellow column = this week
ID | Phase | Task | Room | Contractor | Duration (days) | Predecessor ID | Earliest start (optional) | Start | Delay (days) | End | Status | Done date | Affects N tasks | Flag | code | first | okey | due | pri | text
1 | Pre-construction | Design & plans |  |  | 21 | [5 empty] | Not started
2 | Pre-construction | Building permit |  |  | 28 | 1 |  |  |  |  | Not started
3 | Pre-construction | Contractor selection |  |  | 14 | 1 |  |  |  |  | Not started
4 | Pre-construction | Order long-lead items |  |  | 7 | 3 |  |  |  |  | Not started
5 | Construction | Demolition & strip-out |  |  | 10 | 2 |  |  |  |  | Not started
6 | Construction | Structural works |  |  | 12 | 5 |  |  |  |  | Not started
7 | Construction | Electrical rough-in |  |  | 14 | 6 |  |  |  |  | Not started
8 | Construction | Plumbing rough-in |  |  | 14 | 6 |  |  |  |  | Not started
9 | Construction | Rough-in inspection |  |  | 2 | 8 |  |  |  |  | Not started
10 | Construction | Insulation & walls |  |  | 14 | 9 |  |  |  |  | Not started
11 | Construction | Flooring |  |  | 10 | 10 |  |  |  |  | Not started
12 | Construction | Kitchen installation |  |  | 12 | 10 |  |  |  |  | Not started
13 | Construction | Bathroom fit-out |  |  | 15 | 10 |  |  |  |  | Not started
14 | Construction | Painting & decorating |  |  | 12 | 13 |  |  |  |  | Not started
15 | Final | Final inspection |  |  | 2 | 14 |  |  |  |  | Not started
16 | Final | Punch list |  |  | 10 | 15 |  |  |  |  | Not started
17 | Final | Cleaning |  |  | 3 | 16 |  |  |  |  | Not started
18 | Final | Move-in |  |  | 3 | 17 |  |  |  |  | Not started
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
Note on B6: Fixed task number. Use it in the Predecessor column of later tasks.
Note on G6: Calendar days the task takes.
Note on H6: ID of the task that must finish first. It must be a LOWER ID (a task listed above this one). Leave empty if none.
Note on I6: Optional: the task cannot start before this date (e.g. contractor availability).
Note on J6: Latest of: project start, your earliest start, predecessor end + 1.
Note on K6: Days this task slipped. Everything that depends on it moves too.
Note on O6: How many tasks list this one as predecessor. >0 = on the critical path: a delay here pushes them.

## Rooms
🛋️ Rooms
What this tab does: one card per room — money, progress, decisions and problems. Rename rooms in the yellow title cells; every dropdown follows.
Kitchen |  | Bathroom 1 |  | name | area | budget | committed | paid | t_total | t_done | progress | decisions | open_issues | open_high | late | lvl | c1 | c2 | c3 | per_area | forecast_room
Budget used |  | Budget used
Progress |  | Progress
Tasks done | Late tasks | Tasks done | Late tasks
Decisions waiting | Open issues | Decisions waiting | Open issues
| High-severity |  | High-severity
Contractors |  | Contractors
Bathroom 2 |  | Master bedroom
Budget used |  | Budget used
Progress |  | Progress
Tasks done | Late tasks | Tasks done | Late tasks
Decisions waiting | Open issues | Decisions waiting | Open issues
| High-severity |  | High-severity
Contractors |  | Contractors
Living room |  | Exterior
Budget used |  | Budget used
Progress |  | Progress
Tasks done | Late tasks | Tasks done | Late tasks
Decisions waiting | Open issues | Decisions waiting | Open issues
| High-severity |  | High-severity
Contractors |  | Contractors
Custom room 7 |  | Custom room 8
Budget used |  | Budget used
Progress |  | Progress
Tasks done | Late tasks | Tasks done | Late tasks
Decisions waiting | Open issues | Decisions waiting | Open issues
| High-severity |  | High-severity
Contractors |  | Contractors
Custom room 9 |  | Custom room 10
Budget used |  | Budget used
Progress |  | Progress
Tasks done | Late tasks | Tasks done | Late tasks
Decisions waiting | Open issues | Decisions waiting | Open issues
| High-severity |  | High-severity
Contractors |  | Contractors

## Selections & Orders
🧩 Selections & Orders
What this tab does: every choice you must make (tiles, taps, appliances…) with automatic decide-by and order-by dates so nothing holds up the builders.
Decisions waiting | [5 empty] | Late orders — install at risk |  |  |  |  | Deliveries after install date
Item / decision | Room | Budget category | Option A | Option B | Option C |  | Chosen | Why this option | Supplier | Lead time (days) | Timeline task ID | Needed-on (override) | Needed on | ORDER BY | DECIDE BY | Ordered? | Order date | Expected delivery | Delivered? | Status | lvl | due | pri | text | dec_wait | dec_over | dec_soon | order_now | late_mat | need_order | order_late
Note on K7: Pick A, B or C once decided. Empty = decision still open.
Note on L7: Counts as Materials on the Budget tab.
Note on O7: Days between ordering and delivery (ask the supplier).
Note on P7: ID of the Timeline task that installs this item. Its start date becomes the needed-on date.
Note on Q7: Optional: type a date to override the Timeline date.
Note on S7: Needed-on − lead time − order safety buffer (Start Here).
Note on T7: Order-by − decide-before-order buffer (Start Here).

## Issues & Punch List
🛠️ Issues & Punch List
What this tab does: every problem found on site and every snag for the final punch list — with who fixes it, by when, and what it may cost.
Open — High |  | Open — Medium |  | Open — Low | Open punch items
# | Type | Date found | Room | Description | Responsible | Severity | Next action | Action date | Status | Resolved date | Photo link | open | lvl | due | pri | text | open_cost | open_high | open_punch
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Note on H7: High = safety, structure, water, or blocks other work. Always shows as 🔴.
Note on I7: What it may cost YOU (0 if the contractor pays). Open issue costs are shown as risk on the Budget tab.
Note on N7: Paste a Google Photos / Drive / OneDrive link.

## Vault
🗄️ Vault
What this tab does: an index of every contract, invoice, permit and photo (paste the Drive/OneDrive link) — and a checklist of what is still missing (right →).
DOCUMENTS YOU SHOULD HAVE (signed contractors)
Document / photo | Type | Contractor | Room | Stage | Date | Link (Drive / OneDrive / Dropbox) | Open | Notes | Contractor | Signed? | Contract | Insurance | Quote | Status | lvl
PROJECT DOCUMENTS
Building permit
Plans / drawings
Inspection reports
PHOTO TRACKER — ✓ when a Photo row exists for room + stage
[9 empty] | Room | Before | Demolition | Rough-in | Walls | Finishing | Final
Note on F5: For photos: which stage of the work (feeds the photo tracker).
Note on H5: Paste the share link of the file or folder.

## Warranty & Maintenance
🛡️ Warranty & Maintenance
What this tab does: tracks warranty expiry dates (check for defects before they run out) and recurring home maintenance. Both create alerts.
WARRANTIES
Item / work | Supplier / contractor | Room | Purchase / completion date | Warranty (years) | Expires | Days left | Status | Warranty document link | lvl | due | pri | text
HOME MAINTENANCE
Maintenance task | Room | Every (months) | Last done | Next due | Days left | Status |  |  | lvl | due | pri | text
Note on I6: Expires soon = within 90 days: inspect and report defects now.

## Engine (hidden)
Source tab | Alert | Due | Priority | Sort key | Week key | Rank | Key | Row | Tab | Alert | Due | Priority | Rank | Key | Row | Tab | Alert | Due | Priority |  | Rank | Category | Budget | Forecast
Selections & Orders | [5 empty] | 1 | [6 empty] | 1 | [6 empty] | AlertCount | 1
Selections & Orders | [5 empty] | 2 | [6 empty] | 2 | [6 empty] | OverdueCount | 2
Selections & Orders | [5 empty] | 3 | [6 empty] | 3 | [6 empty] | UrgentCount | 3
Selections & Orders | [5 empty] | 4 | [6 empty] | 4 | [6 empty] | WeekAlertCount | 4
Selections & Orders | [5 empty] | 5 | [6 empty] | 5 | [7 empty] | 5
Selections & Orders | [5 empty] | 6 | [6 empty] | 6 | [7 empty] | 6
Selections & Orders | [5 empty] | 7 | [6 empty] | 7 | [7 empty] | 7
Selections & Orders | [5 empty] | 8 | [6 empty] | 8 | [7 empty] | 8
Selections & Orders | [5 empty] | 9 | [6 empty] | 9 | [7 empty] | 9
Selections & Orders | [5 empty] | 10 | [6 empty] | 10 | [7 empty] | 10
Selections & Orders | [5 empty] | 11 | [6 empty] | 11 | [7 empty] | 11
Selections & Orders | [5 empty] | 12 | [6 empty] | 12 | [7 empty] | 12
Selections & Orders | [5 empty] | 13 | [6 empty] | 13
Selections & Orders | [5 empty] | 14 | [6 empty] | 14
Selections & Orders | [5 empty] | 15 | [6 empty] | 15
Selections & Orders | [5 empty] | 16 | [6 empty] | 16
Selections & Orders | [5 empty] | 17 | [6 empty] | 17
Selections & Orders | [5 empty] | 18 | [6 empty] | 18
Selections & Orders | [5 empty] | 19 | [6 empty] | 19
Selections & Orders | [5 empty] | 20 | [6 empty] | 20
Selections & Orders | [5 empty] | 21 | [6 empty] | 21
Selections & Orders | [5 empty] | 22 | [6 empty] | 22
Selections & Orders | [5 empty] | 23 | [6 empty] | 23
Selections & Orders | [5 empty] | 24 | [6 empty] | 24
Selections & Orders | [5 empty] | 25 | [6 empty] | 25
Selections & Orders
Selections & Orders | [5 empty] | TOP 25 (all) | [6 empty] | TOP 25 (due by week end)
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Selections & Orders
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Quotes
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Change Orders
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Warranty & Maintenance
Budget
Budget

## Lists (hidden)
YesNo | Stage | Incl | COStatus | COReason | ReqBy | Phase | TaskStatus | IssueType | Severity | IssueStatus | DocType | PhotoStage | ABC | Gut | CurLabel | CurSym | TaxName | AreaUnit | WeekStart | WarnBand | Categories | Rooms | Contractors
Yes | Estimating | Included | Pending | Client choice | Owner | Pre-construction | Not started | Issue | Low | Open | Contract | Before | A | 1 | EUR € | € | VAT | m² | Monday | 0%
No | Contracted | Not included | Approved | Unforeseen condition | Contractor | Construction | In progress | Punch item | Medium | In progress | Quote | Demolition | B | 2 | USD $ | $ | Sales tax | ft² | Sunday | 5%
| Complete | Unclear | Rejected | Design change | Architect / designer | Final | Done |  | High | Resolved | Invoice | Rough-in | C | 3 | GBP £ | £ | GST |  |  | 10%
|  |  |  | Code requirement | Inspector | [5 empty] | Permit | Walls |  | 4 | CHF | CHF | HST
|  |  |  | Contractor error | Other | [5 empty] | Plan | Finishing |  | 5 | CAD $ | C$ | TVA
[11 empty] | Insurance | Final |  |  | AUD $ | A$ | MwSt
[11 empty] | Warranty |  |  |  | NZD $ | NZ$ | BTW
[11 empty] | Receipt |  |  |  | SEK kr | kr | IVA
[11 empty] | Photo |  |  |  | NOK kr | kr | None
[11 empty] | Inspection |  |  |  | DKK kr | kr
[11 empty] | Other |  |  |  | PLN zł | zł | [5 empty] | Whole house
[15 empty] | CZK Kč | Kč
Other