## Start Here
🏠 Renovation OS Lite — Start Here
What this tab does: set up your project once (yellow cells), then follow the 5 steps on the right.
© 2026 Renovation OS — created by Hang Nguyen. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
YOUR PROJECT |  |  | GET STARTED IN 10 MINUTES
Project name | Maple Lane Renovation | Shown as the Dashboard title. | 1 | Fill in the yellow cells on the left
Property address | 12 Maple Lane | For your own reference. |  | Project dates, total budget, currency, tax. Everything else calculates itself.
Project start date | 2026-03-02 | First day of the project (design counts!). The Timeline starts here. | 2 | Budget tab: set a budget per category
Target move-in date | 2026-08-21 | The date you want to live in the house again. |  | Rename categories if you like. Aim for the total to match your working budget.
| 135000 | Everything you can spend, including tax and your safety buffer. | 3 | Contractors + Payments: who you pay, and when
| 142 | Optional — used for cost per m² / ft². |  | Enter each contract and its payment milestones — you get a warning if you pay ahead of the work.
“Today” override (optional) | 2026-06-15 | DEMO is frozen on this date so every feature shows data — clear this cell to use today's date. | 4 | Timeline: set durations and dependencies
Dates, the Gantt chart and late-task alerts follow automatically.
PREFERENCES |  |  | 5 | Every Monday open the Dashboard
Currency | EUR € | Shown next to every amount header. Pick ‘Other’ to type your own symbol. |  | Do the ranked actions, top to bottom. That's the whole routine.
Custom currency symbol |  | Only used when Currency = Other.
Tax name | VAT | VAT, Sales tax, GST… used in labels.
Area unit | m² | m² or ft² for room sizes. | COLOUR LEGEND
Week starts on | Monday | Used by This Week and the Gantt chart. |  | Light-yellow cell = YOU TYPE HERE (or pick from the dropdown).
Budget ‘attention’ band | 5% | A budget line turns 🟡 when forecast is over budget by up to this %, 🔴 above. |  | White / grey cell = automatic. Protected so you can't break a formula.
|  |  | 🟢 | On track — nothing to do.
|  |  | 🟡 | Needs attention soon (within your alert window).
|  |  | 🔴 | Urgent — overdue, over budget or at risk.
ALERT SETTINGS |  |  |  | White cells are locked and protected, so a formula can never be broken by accident. Type only in the yellow cells.
Contingency (safety buffer) % | 10% | 10–15% is typical. Kept aside from your total budget.
Alert window (days) | 7 | Things due within this many days show as 🟡 ‘this week’. | YOUR TABS
Overpayment tolerance % | 10% | Warn when paid % is more than this ahead of work done %. | ▸ | Dashboard | Your renovation at a glance + ranked next actions.
|  |  | ▸ | Budget | Budget vs committed vs forecast per category.
|  |  | ▸ | Contractors | Contractors, overpayment check and communication log.
|  |  | ▸ | Payments | Payment schedule, invoices and 12-month cash flow.
CALCULATED FOR YOU |  |  | ▸ | Timeline | Tasks, dependencies and Gantt chart.
|  | Kept aside for surprises — not part of your working budget. | ▸ | Issues & Punch List | Problems found on site and the final punch list.
What you plan to spend. Budget lines should add up to this.
Currency symbol in use |  |  | ⭐ Renovation OS Pro adds: quote comparison with hidden costs, change-order impact preview, decide-by / order-by dates for materials, room cards, This Week planner, document vault and warranty tracker.
Today (as used by all tabs)
Tax word used in labels
LICENCE & TERMS OF USE
© 2026 Renovation OS — created by Hang Nguyen. All rights reserved.
• This file is licensed, not sold, to the original purchaser for personal, non-commercial use on their own home renovation.
• You may NOT share, copy, resell, redistribute, sublicense, give away or upload this file (or any modified version or part of it) to any website, marketplace, group or other person.
• The formulas, structure, layout and design are protected by copyright and belong to Renovation OS. Removing this notice or the sheet protection is not permitted.
• Digital product: all sales are final. No refunds once the file has been delivered.
• Provided “as is” as a planning aid, without warranty. It is not financial, legal or construction advice — always check figures before you act on them.
Note on B9: Your total renovation budget including tax. Renovation OS keeps the contingency % aside as a safety buffer, the rest is your working budget.
Note on B11: Normally empty. Type a date here to see the workbook as it was/will be on that date. The demo file is frozen on a date so every feature shows data.
Note on B24: Money you keep aside for surprises. Working budget = total budget − contingency.
Note on B26: Protects you from paying ahead of progress. Example: 10% means paying 50% for 35% of the work triggers a warning.

## Dashboard
What this tab does: your renovation at a glance — updated automatically. Nothing to type here. |  |  |  |  | As of
© 2026 Renovation OS — created by Hang Nguyen. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
|  |  | Contingency used | Project day |  | Time elapsed
Forecast move-in |  | Open issues | Overdue items | Late tasks |  | Payments due soon
RENOVATION HEALTH
Budget
Timeline
Contractors & payments
Issues
YOUR NEXT ACTIONS — ranked by urgency
# | Priority | What to do |  | Where |  | Due | When
CHARTS

## Budget
💶 Budget
What this tab does: compares your budget per category with what you have committed, invoiced and paid, and forecasts the final cost.
© 2026 Renovation OS — created by Hang Nguyen. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
Sum of category budgets
Category |  | Stage |  | Status | lvl | chart key
Demolition | 4000 | Complete
Structural | 9000 | Complete
Plumbing | 9500 | Contracted
Electrical | 10000 | Contracted
HVAC | 9000 | Contracted
Windows & doors | 12000 | Contracted
Roofing | 3000 | Estimating
Kitchen | 20000 | Contracted
Bathrooms | 15000 | Contracted
Flooring | 8500 | Estimating
Painting | 4500 | Estimating
Landscaping | 2000 | Estimating
Furniture | 3000 | Estimating
Appliances | 3500 | Estimating
Permits | 1500 | Complete
Professional fees | 5000 | Contracted
Waste removal | 1500 | Estimating
Other | 500 | Estimating
TOTAL
RISK — what could still come on top of the forecast
Pending change orders (not approved yet)
Estimated cost of open issues
RISK (could still be added)
FORECAST INCL. RISK
Contingency used by forecast
Note on B7: Rename, add or clear categories (up to 30). They feed every Category dropdown in the workbook.
Note on D7: Estimating = still collecting quotes. Contracted = contract signed. Complete = work finished and final invoice received.
Note on E7: Lowest TRUE cost (incl. hidden costs) from the Quotes tab for this category.
Note on F7: Sum of SIGNED contracts on the Contractors tab with this category.
Note on G7: Materials you buy yourself: selected option prices on Selections & Orders.
Note on H7: Approved change orders for this category.
Note on I7: Signed contracts: money you have promised to spend.
Note on L7: Estimating: the highest of budget, committed and invoiced (be pessimistic until signed). Contracted/Complete: committed (or invoiced if higher).
Note on M7: Budget − forecast. Negative (red) = over budget.

## Contractors
👷 Contractors
What this tab does: one row per contractor — contract, paperwork, progress and a warning when you pay ahead of the work. Communication log on the right →
© 2026 Renovation OS — created by Hang Nguyen. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
💬 Communication log → (scroll right, column AA) | [20 empty] | COMMUNICATION LOG — every call, email and site conversation. Follow-ups turn into alerts.
Company | Trade | Budget category | Main room | Contact person | Phone | Email |  | Contract signed? | Start | Expected completion | Insurance ✓ | License ✓ | Warranty (years) | % work complete | Paid % | Overpayment check | lvl | due | pri | text | Contractor | Date | What was said / agreed | Follow-up needed? | Follow-up date | Follow-up done? | due | pri | text
Hansen Demolition | Demolition & strip-out | Demolition | Whole house | Lars Hansen | +31 6 1234 5678 | lars@hansen-demo.example | 3800 | Yes | 2026-04-20 | 2026-04-29 | Yes | Yes | 1 | 100% | [6 empty] | Bright Spark Electric | 2026-06-02 | Asked for revised schedule after 1-week slip — no reply yet | Yes | 2026-06-10 | No
Solid Structures Ltd | Builder / structural | Structural | Living room | Maria Costa | +31 6 2345 6789 | maria@solidstructures.example | 10600 | Yes | 2026-04-30 | 2026-05-11 | Yes | Yes | 10 | 100% | [6 empty] | Oak & Plank Flooring | 2026-06-12 | Quote received; asked them to include skirting boards | Yes | 2026-06-18 | No
FlowRight Plumbing | Plumbing | Plumbing | Whole house | Tom de Vries | +31 6 3456 7890 | tom@flowright.example | 9200 | Yes | 2026-05-12 | 2026-06-05 | Yes | Yes | 2 | 60% | [6 empty] | Nordic Kitchens | 2026-05-28 | Confirmed install start 2 July, delivery 1 July | No
Bright Spark Electric | Electrical | Electrical | Whole house | Ahmed Karimi | +31 6 4567 8901 | ahmed@brightspark.example | 10500 | Yes | 2026-05-12 | 2026-06-15 | Yes | No | 2 | 35% | [6 empty] | FlowRight Plumbing | 2026-06-09 | Pipe re-routing caused delay; rough-in now late | Yes | 2026-06-01 | Yes
ClimaHeat HVAC | Heat pump & ventilation | HVAC | Whole house | Eva Jansen | +31 6 5678 9012 | eva@climaheat.example | 9300 | Yes | 2026-06-06 | 2026-06-15 | Yes | Yes | 5 | 25%
ClearView Windows | Windows & doors | Windows & doors | Whole house | Pieter Smit | +31 6 6789 0123 | pieter@clearview.example | 12400 | Yes | 2026-04-30 | 2026-05-07 | Yes | Yes | 10 | 90%
Nordic Kitchens | Kitchen supply & install | Kitchen | Kitchen | Sofie Berg | +31 6 7890 1234 | sofie@nordickitchens.example | 20300 | Yes | 2026-07-02 | 2026-07-13 | Yes | Yes | 5 | 0%
Aqua Bath Studio | Bathroom fit-out | Bathrooms | Bathroom 1 | Luca Romano | +31 6 8901 2345 | luca@aquabath.example | 12850 | Yes | 2026-07-02 | 2026-07-26 | Yes | Yes | 5 | 0%
GreenPlan Architects | Architect & permits | Professional fees | Whole house | Nina Visser | +31 6 9012 3456 | nina@greenplan.example | 4800 | Yes | 2026-03-02 | 2026-08-14 | Yes | Yes | 0 | 75%
Finish Line Painters | Painting & decorating | Painting | Whole house | Johan Bakker | +31 6 0123 4567 | johan@finishline.example | 4700 | No |  |  | Yes | Yes | 2 | 0%
Oak & Plank Flooring | Flooring | Flooring | Whole house | Mila Peters | +31 6 1122 3344 | mila@oakplank.example |  | No |  |  | Yes | Yes | 10
StoneWorks | Quartz worktop (supply) | Kitchen | Kitchen | Order desk | +31 20 555 0101 | orders@stoneworks.example | 2450 | Yes | 2026-06-01 | 2026-06-26 | Yes | Yes | 10 | 0%
ApplianceHub | Kitchen appliances (supply) | Appliances | Kitchen | Web shop | +31 20 555 0102 | service@appliancehub.example | 3230 | Yes | 2026-05-25 | 2026-07-08 | Yes | Yes | 2 | 40%
BathWorld | Vanity + shower enclosure (supply) | Bathrooms | Bathroom 1 | Showroom | +31 20 555 0103 | sales@bathworld.example | 2040 | Yes | 2026-05-20 | 2026-06-30 | Yes | Yes | 5 | 55%
Note on D5: Links this contract to a Budget line.
Note on E5: Where most of their work happens (or Whole house). Used by the Rooms tab.
Note on I5: Signed contract amount incl. tax. Add approved extras to it.
Note on L5: Only signed contracts count as Committed on the Budget.
Note on O5: Have you seen a valid liability insurance certificate?
Note on P5: Registered / licensed for this trade where required?
Note on R5: YOUR estimate of how much of their work is done. Update weekly — it drives the overpayment check.
Note on U5: ⚠️ appears when paid % is ahead of work complete % by more than your tolerance (Start Here).

## Payments
💳 Payments
What this tab does: your payment schedule, invoices and payments per contractor — plus a 12-month cash-flow forecast (right side →).
© 2026 Renovation OS — created by Hang Nguyen. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
[21 empty] | PER-CONTRACTOR SUMMARY |  | CASH FLOW — 12 months from project start
Paid to (contractor / supplier) | Milestone / what for | Room (optional) | Category (if not a contractor) | % of contract |  | Due date | Invoice # | Invoice date |  | Paid date |  | Status | Category (auto) | room | lvl | unpaid | 1/due | due | pri | text | Contractor | Next payment
GreenPlan Architects | Design package 50% |  |  | 50% |  | 2026-03-25 | GP-01 | 2026-03-20 | 2400 | 2026-03-24 | 2400
City Building Dept | Building permit fee |  | Permits |  | 1350 | 2026-03-30 | PERMIT-2026-114 | 2026-03-25 | 1350 | 2026-03-28 | 1350 | [11 empty] | Month
GreenPlan Architects | Permit approved 25% |  |  | 25% |  | 2026-04-22 | GP-02 | 2026-04-20 | 1200 | 2026-04-21 | 1200
ClearView Windows | Order 40% |  |  | 40% |  | 2026-04-10 | CV-311 | 2026-04-06 | 4960 | 2026-04-09 | 4960
Hansen Demolition | Deposit 30% |  |  | 30% |  | 2026-04-15 | H-101 | 2026-04-10 | 1140 | 2026-04-14 | 1140
City Skips | Skip hire (2 skips) |  | Waste removal |  | 640 | 2026-04-22 | CS-88 | 2026-04-20 | 640 | 2026-04-22 | 640
Solid Structures Ltd | Deposit 30% |  |  | 30% |  | 2026-04-25 | SS-12 | 2026-04-21 | 2820 | 2026-04-24 | 2820
Hansen Demolition | Completion 70% |  |  | 70% |  | 2026-05-05 | H-107 | 2026-04-30 | 2660 | 2026-05-04 | 2660
Bright Spark Electric | Deposit 30% |  |  | 30% |  | 2026-05-08 | BS-2026-04 | 2026-05-04 | 3150 | 2026-05-07 | 3150
FlowRight Plumbing | Start of works 30% |  |  | 30% |  | 2026-05-12 | FR-5501 | 2026-05-08 | 2760 | 2026-05-11 | 2760
Nordic Kitchens | Deposit 10% | Kitchen |  | 10% |  | 2026-05-15 | NK-778 | 2026-05-11 | 1940 | 2026-05-14 | 1940
ClearView Windows | Installation 50% |  |  | 50% |  | 2026-05-15 | CV-340 | 2026-05-08 | 6200 | 2026-05-14 | 6200
Solid Structures Ltd | Completion 70% |  |  | 70% |  | 2026-05-20 | SS-19 | 2026-05-12 | 6580 | 2026-05-19 | 6580
Solid Structures Ltd | Change order CO-1 (steel beam) |  |  |  | 1200 | 2026-05-25 | SS-20 | 2026-05-18 | 1200 | 2026-05-25 | 1200
Bright Spark Electric | First fix 30% |  |  | 30% |  | 2026-06-01 | BS-2026-07 | 2026-05-26 | 3150 | 2026-05-30 | 3150
ClimaHeat HVAC | Equipment 30% |  |  | 30% |  | 2026-06-05 | CH-90 | 2026-06-01 | 2790 | 2026-06-04 | 2790
FlowRight Plumbing | Rough-in complete 40% |  |  | 40% |  | 2026-06-10 | FR-5534 | 2026-06-01 | 3680
Aqua Bath Studio | Deposit 20% |  |  | 20% |  | 2026-06-19 | ABS-301 | 2026-06-12 | 2240
ClearView Windows | Final 10% (after snagging) |  |  | 10% |  | 2026-06-20 | CV-362 | 2026-06-12 | 1240
TileDepot | Bathroom 1 tiles | Bathroom 1 | Bathrooms |  | 1450 | 2026-06-15 | TD-4471 | 2026-06-12 | 1450 | 2026-06-15 | 1450
StoneWorks | Quartz worktop | Kitchen | Kitchen |  | 2450 | 2026-06-25
Nordic Kitchens | Delivery 50% | Kitchen |  | 50% |  | 2026-06-29
ClimaHeat HVAC | Commissioning 70% |  |  | 70% |  | 2026-06-30
FlowRight Plumbing | Final 30% |  |  | 30% |  | 2026-07-20
Nordic Kitchens | Completion 40% | Kitchen |  | 40% |  | 2026-07-20
Aqua Bath Studio | Completion 80% |  |  | 80% |  | 2026-07-31
Bright Spark Electric | Final 40% |  |  | 40% |  | 2026-08-12
GreenPlan Architects | Final sign-off 25% |  |  | 25% |  | 2026-08-20
Note on B5: Pick a contractor, or type any supplier name (you'll get a warning you can accept).
Note on D5: Leave empty to use the contractor's main room.
Note on E5: Only needed for suppliers that are not on the Contractors tab, so the payment lands on the right Budget line.
Note on F5: Milestone as % of the contract value…
Note on G5: …or a fixed amount (wins over %).
Note on M5: Enter the date you paid — this marks the row as Paid.
Note on AK5: All unpaid amounts due in the next 30 days, including anything overdue.

## Timeline
📅 Timeline
What this tab does: tasks with durations and dependencies → start/end dates, late warnings and a 52-week Gantt chart. Forecast finish feeds the Dashboard.
© 2026 Renovation OS — created by Hang Nguyen. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
| Forecast finish |  | Target move-in | [17 empty] | Gantt: teal = planned · grey = done · red = late · yellow column = this week
ID | Phase | Task | Room | Contractor | Duration (days) | Predecessor ID | Earliest start (optional) | Start | Delay (days) | End | Status | Done date | Affects N tasks | Flag | code | first | okey | due | pri | text
1 | Pre-construction | Design & plans | Whole house | GreenPlan Architects | 21 | [5 empty] | Done | 2026-03-20
2 | Pre-construction | Building permit | Whole house | GreenPlan Architects | 28 | 1 |  |  |  |  | Done | 2026-04-17
3 | Pre-construction | Contractor selection | Whole house |  | 14 | 1 |  |  |  |  | Done | 2026-04-03
4 | Pre-construction | Order long-lead items | Whole house |  | 7 | 3 |  |  |  |  | Done | 2026-04-10
5 | Construction | Demolition & strip-out | Whole house | Hansen Demolition | 10 | 2 |  |  |  |  | Done | 2026-04-29
6 | Construction | Structural beam & walls | Living room | Solid Structures Ltd | 12 | 5 |  |  |  |  | Done | 2026-05-11
7 | Construction | Windows & doors | Whole house | ClearView Windows | 8 | 5 |  |  |  |  | Done | 2026-05-08
8 | Construction | Plumbing rough-in | Bathroom 1 | FlowRight Plumbing | 14 | 6 |  |  | 11 |  | In progress
9 | Construction | Electrical rough-in | Whole house | Bright Spark Electric | 28 | 6 |  |  | 7 |  | In progress
10 | Construction | Heat pump & ventilation | Whole house | ClimaHeat HVAC | 10 | 8 |  |  |  |  | Not started
11 | Construction | Rough-in inspection | Whole house |  | 2 | 9 |  |  |  |  | Not started
12 | Construction | Insulation & drywall | Whole house | Solid Structures Ltd | 14 | 11 |  |  |  |  | Not started
13 | Construction | Flooring | Living room | Oak & Plank Flooring | 10 | 12 |  |  |  |  | Not started
14 | Construction | Kitchen installation | Kitchen | Nordic Kitchens | 12 | 12 |  |  |  |  | Not started
15 | Construction | Bathroom 1 fit-out | Bathroom 1 | Aqua Bath Studio | 15 | 12 |  |  |  |  | Not started
16 | Construction | Bathroom 2 fit-out | Bathroom 2 | Aqua Bath Studio | 10 | 15 |  |  |  |  | Not started
17 | Construction | Painting & decorating | Whole house | Finish Line Painters | 12 | 16 |  |  |  |  | Not started
18 | Construction | Landscaping | Exterior |  | 10 | 7 | 2026-07-20 |  |  |  | Not started
19 | Final | Final electrical & plumbing fixes | Whole house | Bright Spark Electric | 5 | 17 |  |  |  |  | Not started
20 | Final | Final inspection | Whole house |  | 2 | 19 |  |  |  |  | Not started
21 | Final | Punch list | Whole house |  | 10 | 20 |  |  |  |  | Not started
22 | Final | Cleaning | Whole house |  | 3 | 21 |  |  |  |  | Not started
23 | Final | Furniture & move-in | Whole house |  | 5 | 22 |  |  |  |  | Not started
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
Note on B6: Fixed task number. Use it in the Predecessor column of later tasks.
Note on G6: Calendar days the task takes.
Note on H6: ID of the task that must finish first. It must be a LOWER ID (a task listed above this one). Leave empty if none.
Note on I6: Optional: the task cannot start before this date (e.g. contractor availability).
Note on J6: Latest of: project start, your earliest start, predecessor end + 1.
Note on K6: Days this task slipped. Everything that depends on it moves too.
Note on O6: How many tasks list this one as predecessor. >0 = on the critical path: a delay here pushes them.

## Issues & Punch List
🛠️ Issues & Punch List
What this tab does: every problem found on site and every snag for the final punch list — with who fixes it, by when, and what it may cost.
© 2026 Renovation OS — created by Hang Nguyen. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
Open — High |  | Open — Medium |  | Open — Low | Open punch items
# | Type | Date found | Room | Description | Responsible | Severity |  | Next action | Action date | Status | Resolved date | Photo link | open | lvl | due | pri | text | open_cost | open_high | open_punch
1 | Issue | 2026-05-14 | Living room | Rotten joist found under living room floor | Solid Structures Ltd | High | 1800 | Engineer to confirm repair method | 2026-06-12 | Open
2 | Issue | 2026-06-03 | Bathroom 1 | Waste pipe routed through planned shower niche | FlowRight Plumbing | Medium | 350 | Site meeting to agree re-route | 2026-06-17 | In progress
3 | Issue | 2026-06-10 | Kitchen | Socket positions don't match kitchen plan | Bright Spark Electric | Medium | 250 | Send marked-up plan to electrician | 2026-06-11 | Open
4 | Punch item | 2026-05-09 | Master bedroom | Window handle loose | ClearView Windows | Low | 0 | Fix at final visit | 2026-06-20 | Open
5 | Punch item | 2026-06-15 | Living room | Scratch on new sliding door frame | ClearView Windows | Low | 0 | Touch-up at final visit | 2026-06-26 | Open
6 | Issue | 2026-04-22 | Whole house | Asbestos in old floor tiles | Hansen Demolition | High | 1100 | Licensed removal | 2026-04-25 | Resolved | 2026-04-28
7 | Issue | 2026-05-05 | Exterior | Skip blocking neighbour's driveway | Hansen Demolition | Low | 0 | Move skip | 2026-05-06 | Resolved | 2026-05-06
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
264
265
266
267
268
269
270
271
272
273
274
275
276
277
278
279
280
281
282
283
284
285
286
287
288
289
290
291
292
293
294
295
296
297
298
299
300
301
302
303
304
305
306
307
308
309
310
311
312
313
314
315
316
317
318
319
320
321
322
323
324
325
326
327
328
329
330
331
332
333
334
335
336
337
338
339
340
341
342
343
344
345
346
347
348
349
350
351
352
353
354
355
356
357
358
359
360
361
362
363
364
365
366
367
368
369
370
371
372
373
374
375
376
377
378
379
380
381
382
383
384
385
386
387
388
389
390
391
392
393
394
395
396
397
398
399
400
401
402
403
404
405
406
407
408
409
410
411
412
413
414
415
416
417
418
419
420
421
422
423
424
425
426
427
428
429
430
431
432
433
434
435
436
437
438
439
440
441
442
443
444
445
446
447
448
449
450
451
452
453
454
455
456
457
458
459
460
461
462
463
464
465
466
467
468
469
470
471
472
473
474
475
476
477
478
479
480
481
482
483
484
485
486
487
488
489
490
491
492
493
494
495
496
497
498
499
500
501
502
503
504
505
506
507
508
509
510
511
512
513
514
515
516
517
518
519
520
521
522
523
524
525
526
527
528
529
530
531
532
533
534
535
536
537
538
539
540
541
542
543
544
545
546
547
548
549
550
551
552
553
554
555
556
557
558
559
560
561
562
563
564
565
566
567
568
569
570
571
572
573
574
575
576
577
578
579
580
581
582
583
584
585
586
587
588
589
590
591
592
593
594
595
596
597
598
599
600
601
602
603
604
605
606
607
608
609
610
611
612
613
614
615
616
617
618
619
620
621
622
623
624
625
626
627
628
629
630
631
632
633
634
635
636
637
638
639
640
641
642
643
644
645
646
647
648
649
650
651
652
653
654
655
656
657
658
659
660
661
662
663
664
665
666
667
668
669
670
671
672
673
674
675
676
677
678
679
680
681
682
683
684
685
686
687
688
689
690
691
692
693
694
695
696
697
698
699
700
701
702
703
704
705
706
707
708
709
710
711
712
713
714
715
716
717
718
719
720
721
722
723
724
725
726
727
728
729
730
731
732
733
734
735
736
737
738
739
740
741
742
743
744
745
746
747
748
749
750
751
752
753
754
755
756
757
758
759
760
761
762
763
764
765
766
767
768
769
770
771
772
773
774
775
776
777
778
779
780
781
782
783
784
785
786
787
788
789
790
791
792
793
794
795
796
797
798
799
800
801
802
803
804
805
806
807
808
809
810
811
812
813
814
815
816
817
818
819
820
821
822
823
824
825
826
827
828
829
830
831
832
833
834
835
836
837
838
839
840
841
842
843
844
845
846
847
848
849
850
851
852
853
854
855
856
857
858
859
860
861
862
863
864
865
866
867
868
869
870
871
872
873
874
875
876
877
878
879
880
881
882
883
884
885
886
887
888
889
890
891
892
893
894
895
896
897
898
899
900
901
902
903
904
905
906
907
908
909
910
911
912
913
914
915
916
917
918
919
920
921
922
923
924
925
926
927
928
929
930
931
932
933
934
935
936
937
938
939
940
941
942
943
944
945
946
947
948
949
950
951
952
953
954
955
956
957
958
959
960
961
962
963
964
965
966
967
968
969
970
971
972
973
974
975
976
977
978
979
980
981
982
983
984
985
986
987
988
989
990
991
992
993
994
995
996
997
998
999
1000
Note on H7: High = safety, structure, water, or blocks other work. Always shows as 🔴.
Note on I7: What it may cost YOU (0 if the contractor pays). Open issue costs are shown as risk on the Budget tab.
Note on N7: Paste a Google Photos / Drive / OneDrive link.

## Engine (hidden)
Source tab | Alert | Due | Priority | Sort key | Week key | Rank | Key | Row | Tab | Alert | Due | Priority |  | Rank | Category | Budget | Forecast
Payments | [5 empty] | 1 | [6 empty] | AlertCount | 1
Payments | [5 empty] | 2 | [6 empty] | OverdueCount | 2
Payments | [5 empty] | 3 | [6 empty] | UrgentCount | 3
Payments | [5 empty] | 4 | [7 empty] | 4
Payments | [5 empty] | 5 | [7 empty] | 5
Payments | [5 empty] | 6 | [7 empty] | 6
Payments | [5 empty] | 7 | [7 empty] | 7
Payments | [5 empty] | 8 | [7 empty] | 8
Payments | [5 empty] | 9 | [7 empty] | 9
Payments | [5 empty] | 10 | [7 empty] | 10
Payments | [5 empty] | 11 | [7 empty] | 11
Payments | [5 empty] | 12 | [7 empty] | 12
Payments | [5 empty] | 13
Payments | [5 empty] | 14
Payments | [5 empty] | 15
Payments | [5 empty] | 16
Payments | [5 empty] | 17
Payments | [5 empty] | 18
Payments | [5 empty] | 19
Payments | [5 empty] | 20
Payments | [5 empty] | 21
Payments | [5 empty] | 22
Payments | [5 empty] | 23
Payments | [5 empty] | 24
Payments | [5 empty] | 25
Payments
Payments | [5 empty] | TOP 25 (all)
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Budget
Budget

## Lists (hidden)
YesNo | Stage | Incl | COStatus | COReason | ReqBy | Phase | TaskStatus | IssueType | Severity | IssueStatus | DocType | PhotoStage | ABC | Gut | CurLabel | CurSym | TaxName | AreaUnit | WeekStart | WarnBand | Categories | Rooms | Contractors
Yes | Estimating | Included | Pending | Client choice | Owner | Pre-construction | Not started | Issue | Low | Open | Contract | Before | A | 1 | EUR € | € | VAT | m² | Monday | 0% |  | Kitchen
No | Contracted | Not included | Approved | Unforeseen condition | Contractor | Construction | In progress | Punch item | Medium | In progress | Quote | Demolition | B | 2 | USD $ | $ | Sales tax | ft² | Sunday | 5% |  | Bathroom 1
| Complete | Unclear | Rejected | Design change | Architect / designer | Final | Done |  | High | Resolved | Invoice | Rough-in | C | 3 | GBP £ | £ | GST |  |  | 10% |  | Bathroom 2
|  |  |  | Code requirement | Inspector | [5 empty] | Permit | Walls |  | 4 | CHF | CHF | HST |  |  |  |  | Master bedroom
|  |  |  | Contractor error | Other | [5 empty] | Plan | Finishing |  | 5 | CAD $ | C$ | TVA |  |  |  |  | Living room
[11 empty] | Insurance | Final |  |  | AUD $ | A$ | MwSt |  |  |  |  | Exterior
[11 empty] | Warranty |  |  |  | NZD $ | NZ$ | BTW |  |  |  |  | Whole house
[11 empty] | Receipt |  |  |  | SEK kr | kr | IVA
[11 empty] | Photo |  |  |  | NOK kr | kr | None
[11 empty] | Inspection |  |  |  | DKK kr | kr
[11 empty] | Other |  |  |  | PLN zł | zł
[15 empty] | CZK Kč | Kč
Other