## Start Here
🏠 Renovation OS Lite — Start Here
What this tab does: set up your project once (yellow cells), then follow the 5 steps on the right.
© 2026 Hang Nguyen — Renovation OS. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
YOUR PROJECT |  |  | GET STARTED IN 10 MINUTES
Project name | Maple Lane Renovation | Shown as the Dashboard title. | 1 | Fill in the yellow cells on the left
Property address | 12 Maple Lane | For your own reference. |  | Project dates, total budget, currency, tax. Everything else calculates itself.
Project start date | 2026-03-02 | First day of the project (design counts!). The Timeline starts here. | 2 | Budget tab: set a budget per category
Target move-in date | 2026-08-21 | The date you want to live in the house again. |  | Rename categories if you like. Aim for the total to match your working budget.
| 135000 | Everything you can spend, including tax and your safety buffer. | 3 | Contractors + Payments: who you pay, and when
| 142 | Optional — used for cost per m² / ft². |  | Enter each contract and its payment milestones — you get a warning if you pay ahead of the work.
“Today” override (optional) | 2026-06-15 | DEMO is frozen on this date so every feature shows data — clear this cell to use today's date. | 4 | Timeline: set durations and dependencies
Dates, the Gantt chart and late-task alerts follow automatically.
PREFERENCES |  |  | 5 | Every Monday open the Dashboard
Currency | EUR € | Shown next to every amount header. Pick ‘Other’ to type your own symbol. |  | Do the ranked actions, top to bottom. That's the whole routine.
Custom currency symbol |  | Only used when Currency = Other.
Tax name | VAT | VAT, Sales tax, GST… used in labels.
Area unit | m² | m² or ft² for room sizes. | COLOUR LEGEND
Week starts on | Monday | Used by This Week and the Gantt chart. |  | Light-yellow cell = YOU TYPE HERE (or pick from the dropdown).
Budget ‘attention’ band | 5% | A budget line turns 🟡 when forecast is over budget by up to this %, 🔴 above. |  | White / grey cell = automatic. Protected so you can't break a formula.
|  |  | 🟢 | On track — nothing to do.
|  |  | 🟡 | Needs attention soon (within your alert window).
|  |  | 🔴 | Urgent — overdue, over budget or at risk.
ALERT SETTINGS |  |  |  | White cells are locked and protected, so a formula can never be broken by accident. Type only in the yellow cells.
Contingency (safety buffer) % | 10% | 10–15% is typical. Kept aside from your total budget.
Alert window (days) | 7 | Things due within this many days show as 🟡 ‘this week’. | YOUR TABS
Overpayment tolerance % | 10% | Warn when paid % is more than this ahead of work done %. | ▸ | Dashboard | Your renovation at a glance + ranked next actions.
|  |  | ▸ | Budget | Budget vs committed vs forecast per category.
|  |  | ▸ | Contractors | Contractors, overpayment check and communication log.
|  |  | ▸ | Payments | Payment schedule, invoices and 12-month cash flow.
CALCULATED FOR YOU |  |  | ▸ | Timeline | Tasks, dependencies and Gantt chart.
|  | Kept aside for surprises — not part of your working budget. | ▸ | Issues & Punch List | Problems found on site and the final punch list.
What you plan to spend. Budget lines should add up to this.
Currency symbol in use |  |  | ⭐ Renovation OS Pro adds: quote comparison with hidden costs, change-order impact preview, decide-by / order-by dates for materials, room cards, This Week planner, document vault and warranty tracker.
Today (as used by all tabs)
Tax word used in labels
LICENCE & TERMS OF USE
Renovation OS © 2026 Hang Nguyen. All rights reserved.
• This file is licensed, not sold, to the original purchaser for personal, non-commercial use on their own home renovation.
• You may NOT share, copy, resell, redistribute, sublicense, give away or upload this file (or any modified version or part of it) to any website, marketplace, group or other person.
• The formulas, structure, layout and design are the intellectual property of Hang Nguyen. Removing this notice or the sheet protection is not permitted.
• Digital product: all sales are final. No refunds once the file has been delivered.
• Provided “as is” as a planning aid, without warranty. It is not financial, legal or construction advice — always check figures before you act on them.
Note on B9: Your total renovation budget including tax. Renovation OS keeps the contingency % aside as a safety buffer, the rest is your working budget.
Note on B11: Normally empty. Type a date here to see the workbook as it was/will be on that date. The demo file is frozen on a date so every feature shows data.
Note on B24: Money you keep aside for surprises. Working budget = total budget − contingency.
Note on B26: Protects you from paying ahead of progress. Example: 10% means paying 50% for 35% of the work triggers a warning.

## Dashboard
What this tab does: your renovation at a glance — updated automatically. Nothing to type here. |  |  |  |  | As of
© 2026 Hang Nguyen — Renovation OS. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
|  |  | Contingency used | Project day |  | Time elapsed
Forecast move-in |  | Open issues | Overdue items | Late tasks |  | Payments due soon
RENOVATION HEALTH
Budget
Timeline
Contractors & payments
Issues
YOUR NEXT ACTIONS — ranked by urgency
# | Priority | What to do |  | Where |  | Due | When
CHARTS

## Budget
💶 Budget
What this tab does: compares your budget per category with what you have committed, invoiced and paid, and forecasts the final cost.
© 2026 Hang Nguyen — Renovation OS. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
Sum of category budgets
Category |  | Stage |  | Status | lvl | chart key
Demolition | 4000 | Complete
Structural | 9000 | Complete
Plumbing | 9500 | Contracted
Electrical | 10000 | Contracted
HVAC | 9000 | Contracted
Windows & doors | 12000 | Contracted
Roofing | 3000 | Estimating
Kitchen | 20000 | Contracted
Bathrooms | 15000 | Contracted
Flooring | 8500 | Estimating
Painting | 4500 | Estimating
Landscaping | 2000 | Estimating
Furniture | 3000 | Estimating
Appliances | 3500 | Estimating
Permits | 1500 | Complete
Professional fees | 5000 | Contracted
Waste removal | 1500 | Estimating
Other | 500 | Estimating
TOTAL
RISK — what could still come on top of the forecast
Pending change orders (not approved yet)
Estimated cost of open issues
RISK (could still be added)
FORECAST INCL. RISK
Contingency used by forecast
Note on B7: Rename, add or clear categories (up to 30). They feed every Category dropdown in the workbook.
Note on D7: Estimating = still collecting quotes. Contracted = contract signed. Complete = work finished and final invoice received.
Note on E7: Lowest TRUE cost (incl. hidden costs) from the Quotes tab for this category.
Note on F7: Sum of SIGNED contracts on the Contractors tab with this category.
Note on G7: Materials you buy yourself: selected option prices on Selections & Orders.
Note on H7: Approved change orders for this category.
Note on I7: Signed contracts: money you have promised to spend.
Note on L7: Estimating: the highest of budget, committed and invoiced (be pessimistic until signed). Contracted/Complete: committed (or invoiced if higher).
Note on M7: Budget − forecast. Negative (red) = over budget.

## Contractors
👷 Contractors
What this tab does: one row per contractor — contract, paperwork, progress and a warning when you pay ahead of the work. Communication log below.
© 2026 Hang Nguyen — Renovation OS. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
Company | Trade | Budget category | Main room | Contact person | Phone | Email |  |  |  | Contract signed? | Start | Expected completion | Insurance ✓ | License ✓ | Warranty (years) | % work complete | Paid % | Overpayment check | lvl | due | pri | text
Hansen Demolition | Demolition & strip-out | Demolition | Whole house | Lars Hansen | +31 6 1234 5678 | lars@hansen-demo.example | 3800 |  |  | Yes | 2026-04-20 | 2026-04-29 | Yes | Yes | 1 | 100%
Solid Structures Ltd | Builder / structural | Structural | Living room | Maria Costa | +31 6 2345 6789 | maria@solidstructures.example | 10600 |  |  | Yes | 2026-04-30 | 2026-05-11 | Yes | Yes | 10 | 100%
FlowRight Plumbing | Plumbing | Plumbing | Whole house | Tom de Vries | +31 6 3456 7890 | tom@flowright.example | 9200 |  |  | Yes | 2026-05-12 | 2026-06-05 | Yes | Yes | 2 | 60%
Bright Spark Electric | Electrical | Electrical | Whole house | Ahmed Karimi | +31 6 4567 8901 | ahmed@brightspark.example | 10500 |  |  | Yes | 2026-05-12 | 2026-06-15 | Yes | No | 2 | 35%
ClimaHeat HVAC | Heat pump & ventilation | HVAC | Whole house | Eva Jansen | +31 6 5678 9012 | eva@climaheat.example | 9300 |  |  | Yes | 2026-06-06 | 2026-06-15 | Yes | Yes | 5 | 25%
ClearView Windows | Windows & doors | Windows & doors | Whole house | Pieter Smit | +31 6 6789 0123 | pieter@clearview.example | 12400 |  |  | Yes | 2026-04-30 | 2026-05-07 | Yes | Yes | 10 | 90%
Nordic Kitchens | Kitchen supply & install | Kitchen | Kitchen | Sofie Berg | +31 6 7890 1234 | sofie@nordickitchens.example | 20300 |  |  | Yes | 2026-07-02 | 2026-07-13 | Yes | Yes | 5 | 0%
Aqua Bath Studio | Bathroom fit-out | Bathrooms | Bathroom 1 | Luca Romano | +31 6 8901 2345 | luca@aquabath.example | 12850 |  |  | Yes | 2026-07-02 | 2026-07-26 | Yes | Yes | 5 | 0%
GreenPlan Architects | Architect & permits | Professional fees | Whole house | Nina Visser | +31 6 9012 3456 | nina@greenplan.example | 4800 |  |  | Yes | 2026-03-02 | 2026-08-14 | Yes | Yes | 0 | 75%
Finish Line Painters | Painting & decorating | Painting | Whole house | Johan Bakker | +31 6 0123 4567 | johan@finishline.example | 4700 |  |  | No |  |  | Yes | Yes | 2 | 0%
Oak & Plank Flooring | Flooring | Flooring | Whole house | Mila Peters | +31 6 1122 3344 | mila@oakplank.example |  |  |  | No |  |  | Yes | Yes | 10
StoneWorks | Quartz worktop (supply) | Kitchen | Kitchen | Order desk | +31 20 555 0101 | orders@stoneworks.example | 2450 |  |  | Yes | 2026-06-01 | 2026-06-26 | Yes | Yes | 10 | 0%
ApplianceHub | Kitchen appliances (supply) | Appliances | Kitchen | Web shop | +31 20 555 0102 | service@appliancehub.example | 3230 |  |  | Yes | 2026-05-25 | 2026-07-08 | Yes | Yes | 2 | 40%
BathWorld | Vanity + shower enclosure (supply) | Bathrooms | Bathroom 1 | Showroom | +31 20 555 0103 | sales@bathworld.example | 2040 |  |  | Yes | 2026-05-20 | 2026-06-30 | Yes | Yes | 5 | 55%
COMMUNICATION LOG — every call, email and site conversation. Follow-ups turn into alerts.
Contractor | Date | What was said / agreed |  |  |  |  | Follow-up needed? | Follow-up date | Follow-up done? | [10 empty] | due | pri | text
Bright Spark Electric | 2026-06-02 | Asked for revised schedule after 1-week slip — no reply yet |  |  |  |  | Yes | 2026-06-10 | No
Oak & Plank Flooring | 2026-06-12 | Quote received; asked them to include skirting boards |  |  |  |  | Yes | 2026-06-18 | No
Nordic Kitchens | 2026-05-28 | Confirmed install start 2 July, delivery 1 July |  |  |  |  | No
FlowRight Plumbing | 2026-06-09 | Pipe re-routing caused delay; rough-in now late |  |  |  |  | Yes | 2026-06-01 | Yes
Note on D5: Links this contract to a Budget line.
Note on E5: Where most of their work happens (or Whole house). Used by the Rooms tab.
Note on I5: Signed contract amount incl. tax. Add approved extras to it.
Note on L5: Only signed contracts count as Committed on the Budget.
Note on O5: Have you seen a valid liability insurance certificate?
Note on P5: Registered / licensed for this trade where required?
Note on R5: YOUR estimate of how much of their work is done. Update weekly — it drives the overpayment check.
Note on U5: ⚠️ appears when paid % is ahead of work complete % by more than your tolerance (Start Here).

## Payments
💳 Payments
What this tab does: your payment schedule, invoices and payments per contractor — plus a 12-month cash-flow forecast (right side →).
© 2026 Hang Nguyen — Renovation OS. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
PER-CONTRACTOR SUMMARY
Paid to (contractor / supplier) | Milestone / what for | Room (optional) | Category (if not a contractor) | % of contract |  | Due date | Invoice # | Invoice date |  | Paid date |  | Status | Category (auto) | room | lvl | unpaid | 1/due | due | pri | text | Contractor | Next payment
GreenPlan Architects | Design package 50% |  |  | 50% |  | 2026-03-25 | GP-01 | 2026-03-20 | 2400 | 2026-03-24 | 2400
City Building Dept | Building permit fee |  | Permits |  | 1350 | 2026-03-30 | PERMIT-2026-114 | 2026-03-25 | 1350 | 2026-03-28 | 1350
GreenPlan Architects | Permit approved 25% |  |  | 25% |  | 2026-04-22 | GP-02 | 2026-04-20 | 1200 | 2026-04-21 | 1200
ClearView Windows | Order 40% |  |  | 40% |  | 2026-04-10 | CV-311 | 2026-04-06 | 4960 | 2026-04-09 | 4960
Hansen Demolition | Deposit 30% |  |  | 30% |  | 2026-04-15 | H-101 | 2026-04-10 | 1140 | 2026-04-14 | 1140
City Skips | Skip hire (2 skips) |  | Waste removal |  | 640 | 2026-04-22 | CS-88 | 2026-04-20 | 640 | 2026-04-22 | 640
Solid Structures Ltd | Deposit 30% |  |  | 30% |  | 2026-04-25 | SS-12 | 2026-04-21 | 2820 | 2026-04-24 | 2820
Hansen Demolition | Completion 70% |  |  | 70% |  | 2026-05-05 | H-107 | 2026-04-30 | 2660 | 2026-05-04 | 2660
Bright Spark Electric | Deposit 30% |  |  | 30% |  | 2026-05-08 | BS-2026-04 | 2026-05-04 | 3150 | 2026-05-07 | 3150
FlowRight Plumbing | Start of works 30% |  |  | 30% |  | 2026-05-12 | FR-5501 | 2026-05-08 | 2760 | 2026-05-11 | 2760
Nordic Kitchens | Deposit 10% | Kitchen |  | 10% |  | 2026-05-15 | NK-778 | 2026-05-11 | 1940 | 2026-05-14 | 1940
ClearView Windows | Installation 50% |  |  | 50% |  | 2026-05-15 | CV-340 | 2026-05-08 | 6200 | 2026-05-14 | 6200
Solid Structures Ltd | Completion 70% |  |  | 70% |  | 2026-05-20 | SS-19 | 2026-05-12 | 6580 | 2026-05-19 | 6580
Solid Structures Ltd | Change order CO-1 (steel beam) |  |  |  | 1200 | 2026-05-25 | SS-20 | 2026-05-18 | 1200 | 2026-05-25 | 1200
Bright Spark Electric | First fix 30% |  |  | 30% |  | 2026-06-01 | BS-2026-07 | 2026-05-26 | 3150 | 2026-05-30 | 3150
ClimaHeat HVAC | Equipment 30% |  |  | 30% |  | 2026-06-05 | CH-90 | 2026-06-01 | 2790 | 2026-06-04 | 2790
FlowRight Plumbing | Rough-in complete 40% |  |  | 40% |  | 2026-06-10 | FR-5534 | 2026-06-01 | 3680
Aqua Bath Studio | Deposit 20% |  |  | 20% |  | 2026-06-19 | ABS-301 | 2026-06-12 | 2240
ClearView Windows | Final 10% (after snagging) |  |  | 10% |  | 2026-06-20 | CV-362 | 2026-06-12 | 1240
TileDepot | Bathroom 1 tiles | Bathroom 1 | Bathrooms |  | 1450 | 2026-06-15 | TD-4471 | 2026-06-12 | 1450 | 2026-06-15 | 1450
StoneWorks | Quartz worktop | Kitchen | Kitchen |  | 2450 | 2026-06-25
Nordic Kitchens | Delivery 50% | Kitchen |  | 50% |  | 2026-06-29
ClimaHeat HVAC | Commissioning 70% |  |  | 70% |  | 2026-06-30
FlowRight Plumbing | Final 30% |  |  | 30% |  | 2026-07-20
Nordic Kitchens | Completion 40% | Kitchen |  | 40% |  | 2026-07-20
Aqua Bath Studio | Completion 80% |  |  | 80% |  | 2026-07-31
Bright Spark Electric | Final 40% |  |  | 40% |  | 2026-08-12
GreenPlan Architects | Final sign-off 25% |  |  | 25% |  | 2026-08-20
CASH FLOW — 12 months from project start
Month
Note on B5: Pick a contractor, or type any supplier name (you'll get a warning you can accept).
Note on D5: Leave empty to use the contractor's main room.
Note on E5: Only needed for suppliers that are not on the Contractors tab, so the payment lands on the right Budget line.
Note on F5: Milestone as % of the contract value…
Note on G5: …or a fixed amount (wins over %).
Note on M5: Enter the date you paid — this marks the row as Paid.
Note on AC38: All unpaid amounts due in the next 30 days, including anything overdue.

## Timeline
📅 Timeline
What this tab does: tasks with durations and dependencies → start/end dates, late warnings and a 52-week Gantt chart. Forecast finish feeds the Dashboard.
© 2026 Hang Nguyen — Renovation OS. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
| Forecast finish |  | Target move-in | [17 empty] | Gantt: teal = planned · grey = done · red = late · yellow column = this week
ID | Phase | Task | Room | Contractor | Duration (days) | Predecessor ID | Earliest start (optional) | Start | Delay (days) | End | Status | Done date | Affects N tasks | Flag | code | first | okey | due | pri | text
1 | Pre-construction | Design & plans | Whole house | GreenPlan Architects | 21 | [5 empty] | Done | 2026-03-20
2 | Pre-construction | Building permit | Whole house | GreenPlan Architects | 28 | 1 |  |  |  |  | Done | 2026-04-17
3 | Pre-construction | Contractor selection | Whole house |  | 14 | 1 |  |  |  |  | Done | 2026-04-03
4 | Pre-construction | Order long-lead items | Whole house |  | 7 | 3 |  |  |  |  | Done | 2026-04-10
5 | Construction | Demolition & strip-out | Whole house | Hansen Demolition | 10 | 2 |  |  |  |  | Done | 2026-04-29
6 | Construction | Structural beam & walls | Living room | Solid Structures Ltd | 12 | 5 |  |  |  |  | Done | 2026-05-11
7 | Construction | Windows & doors | Whole house | ClearView Windows | 8 | 5 |  |  |  |  | Done | 2026-05-08
8 | Construction | Plumbing rough-in | Bathroom 1 | FlowRight Plumbing | 14 | 6 |  |  | 11 |  | In progress
9 | Construction | Electrical rough-in | Whole house | Bright Spark Electric | 28 | 6 |  |  | 7 |  | In progress
10 | Construction | Heat pump & ventilation | Whole house | ClimaHeat HVAC | 10 | 8 |  |  |  |  | Not started
11 | Construction | Rough-in inspection | Whole house |  | 2 | 9 |  |  |  |  | Not started
12 | Construction | Insulation & drywall | Whole house | Solid Structures Ltd | 14 | 11 |  |  |  |  | Not started
13 | Construction | Flooring | Living room | Oak & Plank Flooring | 10 | 12 |  |  |  |  | Not started
14 | Construction | Kitchen installation | Kitchen | Nordic Kitchens | 12 | 12 |  |  |  |  | Not started
15 | Construction | Bathroom 1 fit-out | Bathroom 1 | Aqua Bath Studio | 15 | 12 |  |  |  |  | Not started
16 | Construction | Bathroom 2 fit-out | Bathroom 2 | Aqua Bath Studio | 10 | 15 |  |  |  |  | Not started
17 | Construction | Painting & decorating | Whole house | Finish Line Painters | 12 | 16 |  |  |  |  | Not started
18 | Construction | Landscaping | Exterior |  | 10 | 7 | 2026-07-20 |  |  |  | Not started
19 | Final | Final electrical & plumbing fixes | Whole house | Bright Spark Electric | 5 | 17 |  |  |  |  | Not started
20 | Final | Final inspection | Whole house |  | 2 | 19 |  |  |  |  | Not started
21 | Final | Punch list | Whole house |  | 10 | 20 |  |  |  |  | Not started
22 | Final | Cleaning | Whole house |  | 3 | 21 |  |  |  |  | Not started
23 | Final | Furniture & move-in | Whole house |  | 5 | 22 |  |  |  |  | Not started
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
Note on B6: Fixed task number. Use it in the Predecessor column of later tasks.
Note on G6: Calendar days the task takes.
Note on H6: ID of the task that must finish first. It must be a LOWER ID (a task listed above this one). Leave empty if none.
Note on I6: Optional: the task cannot start before this date (e.g. contractor availability).
Note on J6: Latest of: project start, your earliest start, predecessor end + 1.
Note on K6: Days this task slipped. Everything that depends on it moves too.
Note on O6: How many tasks list this one as predecessor. >0 = on the critical path: a delay here pushes them.

## Issues & Punch List
🛠️ Issues & Punch List
What this tab does: every problem found on site and every snag for the final punch list — with who fixes it, by when, and what it may cost.
© 2026 Hang Nguyen — Renovation OS. Licensed to the original purchaser for personal use only. Do not share, copy, resell or redistribute.
Open — High |  | Open — Medium |  | Open — Low | Open punch items
# | Type | Date found | Room | Description | Responsible | Severity |  | Next action | Action date | Status | Resolved date | Photo link | open | lvl | due | pri | text | open_cost | open_high | open_punch
1 | Issue | 2026-05-14 | Living room | Rotten joist found under living room floor | Solid Structures Ltd | High | 1800 | Engineer to confirm repair method | 2026-06-12 | Open
2 | Issue | 2026-06-03 | Bathroom 1 | Waste pipe routed through planned shower niche | FlowRight Plumbing | Medium | 350 | Site meeting to agree re-route | 2026-06-17 | In progress
3 | Issue | 2026-06-10 | Kitchen | Socket positions don't match kitchen plan | Bright Spark Electric | Medium | 250 | Send marked-up plan to electrician | 2026-06-11 | Open
4 | Punch item | 2026-05-09 | Master bedroom | Window handle loose | ClearView Windows | Low | 0 | Fix at final visit | 2026-06-20 | Open
5 | Punch item | 2026-06-15 | Living room | Scratch on new sliding door frame | ClearView Windows | Low | 0 | Touch-up at final visit | 2026-06-26 | Open
6 | Issue | 2026-04-22 | Whole house | Asbestos in old floor tiles | Hansen Demolition | High | 1100 | Licensed removal | 2026-04-25 | Resolved | 2026-04-28
7 | Issue | 2026-05-05 | Exterior | Skip blocking neighbour's driveway | Hansen Demolition | Low | 0 | Move skip | 2026-05-06 | Resolved | 2026-05-06
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
Note on H7: High = safety, structure, water, or blocks other work. Always shows as 🔴.
Note on I7: What it may cost YOU (0 if the contractor pays). Open issue costs are shown as risk on the Budget tab.
Note on N7: Paste a Google Photos / Drive / OneDrive link.

## Engine (hidden)
Source tab | Alert | Due | Priority | Sort key | Week key | Rank | Key | Row | Tab | Alert | Due | Priority |  | Rank | Category | Budget | Forecast
Payments | [5 empty] | 1 | [6 empty] | AlertCount | 1
Payments | [5 empty] | 2 | [6 empty] | OverdueCount | 2
Payments | [5 empty] | 3 | [6 empty] | UrgentCount | 3
Payments | [5 empty] | 4 | [7 empty] | 4
Payments | [5 empty] | 5 | [7 empty] | 5
Payments | [5 empty] | 6 | [7 empty] | 6
Payments | [5 empty] | 7 | [7 empty] | 7
Payments | [5 empty] | 8 | [7 empty] | 8
Payments | [5 empty] | 9 | [7 empty] | 9
Payments | [5 empty] | 10 | [7 empty] | 10
Payments | [5 empty] | 11 | [7 empty] | 11
Payments | [5 empty] | 12 | [7 empty] | 12
Payments | [5 empty] | 13
Payments | [5 empty] | 14
Payments | [5 empty] | 15
Payments | [5 empty] | 16
Payments | [5 empty] | 17
Payments | [5 empty] | 18
Payments | [5 empty] | 19
Payments | [5 empty] | 20
Payments | [5 empty] | 21
Payments | [5 empty] | 22
Payments | [5 empty] | 23
Payments | [5 empty] | 24
Payments | [5 empty] | 25
Payments
Payments | [5 empty] | TOP 25 (all)
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Payments
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Timeline
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Contractors
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Issues & Punch List
Budget
Budget

## Lists (hidden)
YesNo | Stage | Incl | COStatus | COReason | ReqBy | Phase | TaskStatus | IssueType | Severity | IssueStatus | DocType | PhotoStage | ABC | Gut | CurLabel | CurSym | TaxName | AreaUnit | WeekStart | WarnBand | Categories | Rooms | Contractors
Yes | Estimating | Included | Pending | Client choice | Owner | Pre-construction | Not started | Issue | Low | Open | Contract | Before | A | 1 | EUR € | € | VAT | m² | Monday | 0% |  | Kitchen
No | Contracted | Not included | Approved | Unforeseen condition | Contractor | Construction | In progress | Punch item | Medium | In progress | Quote | Demolition | B | 2 | USD $ | $ | Sales tax | ft² | Sunday | 5% |  | Bathroom 1
| Complete | Unclear | Rejected | Design change | Architect / designer | Final | Done |  | High | Resolved | Invoice | Rough-in | C | 3 | GBP £ | £ | GST |  |  | 10% |  | Bathroom 2
|  |  |  | Code requirement | Inspector | [5 empty] | Permit | Walls |  | 4 | CHF | CHF | HST |  |  |  |  | Master bedroom
|  |  |  | Contractor error | Other | [5 empty] | Plan | Finishing |  | 5 | CAD $ | C$ | TVA |  |  |  |  | Living room
[11 empty] | Insurance | Final |  |  | AUD $ | A$ | MwSt |  |  |  |  | Exterior
[11 empty] | Warranty |  |  |  | NZD $ | NZ$ | BTW |  |  |  |  | Whole house
[11 empty] | Receipt |  |  |  | SEK kr | kr | IVA
[11 empty] | Photo |  |  |  | NOK kr | kr | None
[11 empty] | Inspection |  |  |  | DKK kr | kr
[11 empty] | Other |  |  |  | PLN zł | zł
[15 empty] | CZK Kč | Kč
Other